|  |  |
| --- | --- |
| DIA Urban Arts Projects | * Artwork fabrication in progress
* Skyway columns site prep begins Feb. 25
* 34 artworks to be installed by March 31, 2017
* April Dedication Ceremony TBA
 |
| Courthouse Art Project | * Transfer of funds from reserves into the Art Trust Fund is complete
* Project Overview – APPC March meeting
* Convene first Art Selection Panel meeting TBA
 |
| Law and Liberty | * Seeking budget cost estimates for reinstallation of the two bronze figures in the new Duval county courthouse in progress
 |
| Water Street Parking Garage | * Artist Contract draft is currently under COJ review
* The Design Proposal phase will be initiated following contract approval
* Anticipated due date for Design Proposals is May 1, 2017
 |
| Cuba Hunter Park | * Awaiting approved transfer of funds from reserves into Art Trust Fund
* Project Overview – APPC March meeting
* Art Selection Panel formation is in progress
 |
| Winton Drive | * Input has been received from CM Brown regarding scope of work
* A site visit was completed in November
* Project Overview – APPC March meeting
* Art Selection Panel formation is in progress
 |
| Haskell Downtown Sculpture Initiative | * Fabrication of the sculpture for One Enterprise Center (Water/Hogan St.)

is in progress* Fabrication for a second sculpture at Main/Adams Street is in progress
* An Artist has been selected for a third sculpture at Laura/Forsyth. Site approvals by City Departments are in progress
 |
| Conservation and Maintenance | * Two comprehensive reports have been completed for city-owned public art and memorials
* A Request for Proposals draft is in progress to identify an experienced conservator to complete maintenance and conservation needs identified in the reports
* Anticipated Maintenance and Conservation work will begin summer of 2017
 |
| Collections Management | * A 155-page appraisal report was completed in December for 23 city-owned artworks and memorials
* The report is currently under review by the City’s Risk Management Division in order to add the 23 works to the existing APP collection
 |
| Liberty Street Artwork Removal | * In January, “The Memorial to the Great Fire” and the two bronze River Runners on the Northbank Riverwalk were deinstalled as a result of the COJ Liberty Street construction project.
* The contractor was provided deinstallation, storage and resinstallation recommendations from APP.
* The artworks will be reinstalled back in their original locations in 2018.
 |